## Sheet1
Gantt Chart
Project Timeline
| Project Start Date: | 2022-12-21
|  | Project Name: | Temperature Based Automatic Watering of Crops
[10 empty] | December 21 2022 -January 20 2023 | [7 empty] | December 21 2022 -January 20 2024
[11 empty] | 2022-12-21 | 2022-12-22 | 2023-12-23 | 2023-12-24 | 2023-12-25 | 2023-12-26 | 2023-12-27 | 2023-12-28 | 2023-12-29 | 2023-12-30 | 2023-12-31 | 2024-01-01 | 2024-01-02 | 2024-01-03 | 2024-01-04 | 2024-01-05 | 2024-01-06 | 2024-01-07 | 2024-01-08 | 2024-01-09 | 2024-01-10
|  |  | # | Activity | Start | End | Days | Status | %Done | Sat | Sun | Mon | Tues | Wed | Thurs | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
|  |  | 1 | Creation of WebApp | 2022-12-21 | 2022-12-26 | 6 | Ongoing | 0% | bar: 2022-12-21 to 2024-01-04
|  |  | 2 | Documentation | 2022-12-26 | 2023-01-02 | 6 | Ongoing | 0% | bar: 2022-12-21 to 2024-01-04
|  |  | 3 | Case Test | 2023-01-02 | 2023-01-09 | 6 | Ongoing | 0% | bar: 2022-12-21 to 2024-01-04
|  | Legend |  |  | Team Members: | Assigned Tasks
|  | Done |  |  | Cruz | Documentation
|  | Planning |  |  | Dominguez
|  | Ongoing |  |  | Macadangdang | Creation of WebApp
|  | Behind Plan |  |  | Marcelino
|  | Sundays |  |  | Ong
Burndown Chart
|  |  | Tasks | Estimated Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28 | Day 29 | Day 30 | Day 31 | Hours Left
|  |  | Creation of WebApp | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48
|  |  | Documentation | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
|  |  | Case Test | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
|  |  | Setting | Start | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22 | Day 23 | Day 24 | Day 25 | Day 26 | Day 27 | Day 28 | Day 29 | Day 30 | Day 31
|  |  | Estimated Hours | 48 | 48 | 46 | 44 | 42 | 42 | 40 | 38 | 38 | 37 | 37 | 36 | 36 | 36 | 35 | 34 | 33 | 32 | 31 | 30 | 29 | 25 | 23 | 20 | 17 | 17 | 15 | 13 | 10 | 7 | 4 | 0
|  |  | Actual Hours | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48 | 48